## Task_Table1
Indicators | Task_Mode | Name | Duration | Start_Date | Finish_Date | Priority | Resource_Names | Percent_Complete
| Manually Scheduled | Project initialization | 1 day | 30 March 2019 8 00 AM | 30 March 2019 5 00 PM | 500 | toàn | 1
| Auto Scheduled | Database | 2 days | 31 March 2019 8 00 AM | 02 April 2019 5 00 PM | 500 |  | 1
| Manually Scheduled | Database construction (Entities) | 2 days | 31 March 2019 8 00 AM | 01 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | Input template data | 1 day | 02 April 2019 8 00 AM | 02 April 2019 5 00 PM | 500 | toàn | 1
| Auto Scheduled | Back-end | 19 days | 02 April 2019 8 00 AM | 27 April 2019 5 00 PM | 500 |  | 0.66000000000000003
| Manually Scheduled | DAO | 2 days | 02 April 2019 8 00 AM | 03 April 2019 5 00 PM | 500 | Việt | 1
| Manually Scheduled | Service | 2 days | 04 April 2019 8 00 AM | 05 April 2019 5 00 PM | 500 | Việt | 1
| Auto Scheduled | Controller | 18 days | 03 April 2019 8 00 AM | 27 April 2019 5 00 PM | 500 |  | 0.63
| Auto Scheduled | Customer site | 18 days | 03 April 2019 8 00 AM | 27 April 2019 5 00 PM | 500 |  | 1
| Manually Scheduled | HomeController | 1 day | 03 April 2019 8 00 AM | 03 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | LoginController | 1 day | 04 April 2019 8 00 AM | 04 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | RegistrationController | 1 day | 05 April 2019 8 00 AM | 05 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | ProductController | 2 days | 06 April 2019 8 00 AM | 07 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | ProductDetailController | 2 days | 08 April 2019 8 00 AM | 09 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | CartController | 2 days | 10 April 2019 8 00 AM | 11 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | ContactController | 1 day | 12 April 2019 8 00 AM | 12 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | TrackOrderController | 2 days | 13 April 2019 8 00 AM | 14 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | IntroduceController | 1 day | 15 April 2019 8 00 AM | 15 April 2019 5 00 PM | 500 | toàn | 1
| Auto Scheduled | User site (after login) | 8 days | 16 April 2019 8 00 AM | 25 April 2019 5 00 PM | 500 |  | 1
| Manually Scheduled | UserHomeController | 2 days | 16 April 2019 8 00 AM | 17 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | UserEditInfomationController | 2 days | 18 April 2019 8 00 AM | 19 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | UserFavoriteController | 2 days | 20 April 2019 8 00 AM | 21 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | UserOrderHistoryController | 2 days | 22 April 2019 8 00 AM | 23 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | UserOrderDetailController | 2 days | 24 April 2019 8 00 AM | 25 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | NewsController | 1 day | 26 April 2019 8 00 AM | 26 April 2019 5 00 PM | 500 | toàn | 1
| Manually Scheduled | NewsDetailController | 1 day | 27 April 2019 8 00 AM | 27 April 2019 5 00 PM | 500 | toàn | 1
| Auto Scheduled | Admin site | 12 days | 06 April 2019 8 00 AM | 23 April 2019 5 00 PM | 500 |  | 0.11
| Manually Scheduled | AdminHomeController | 2 days | 06 April 2019 8 00 AM | 07 April 2019 5 00 PM | 500 | Việt | 0
| Manually Scheduled | ProductManagementController | 2 days | 08 April 2019 8 00 AM | 09 April 2019 5 00 PM | 500 | Việt | 0
| Manually Scheduled | CustomerOrdersController | 2 days | 10 April 2019 8 00 AM | 11 April 2019 5 00 PM | 500 | Việt | 0
| Manually Scheduled | OutcomeStatisticController | 2 days | 12 April 2019 8 00 AM | 13 April 2019 5 00 PM | 500 | Việt | 0
| Manually Scheduled | CategoryController | 2 days | 14 April 2019 8 00 AM | 15 April 2019 5 00 PM | 500 | Việt | 0
| Manually Scheduled | AuthorController | 2 days | 16 April 2019 8 00 AM | 17 April 2019 5 00 PM | 500 | Việt | 0
| Manually Scheduled | PublishingCompanyController | 2 days | 18 April 2019 8 00 AM | 19 April 2019 5 00 PM | 500 | Việt | 0
| Manually Scheduled | UserController | 2 days | 20 April 2019 8 00 AM | 21 April 2019 5 00 PM | 500 | Việt | 0
| Manually Scheduled | ContactMangementController | 2 days | 22 April 2019 8 00 AM | 23 April 2019 5 00 PM | 500 | Việt | 1
| Auto Scheduled | Front-end: | 17 days? | 30 March 2019 8 00 AM | 23 April 2019 5 00 PM | 500 |  | 0.67000000000000004
| Auto Scheduled | Customer site | 11 days? | 30 March 2019 8 00 AM | 15 April 2019 5 00 PM | 500 |  | 1
| Manually Scheduled | Home page | 2 days | 30 March 2019 8 00 AM | 31 March 2019 5 00 PM | 500 | tiến | 1
| Manually Scheduled | Login page | 1 day | 01 April 2019 8 00 AM | 01 April 2019 5 00 PM | 500 | tiến | 1
| Manually Scheduled | Registration page | 2 days | 02 April 2019 8 00 AM | 03 April 2019 5 00 PM | 500 | tiến | 1
| Manually Scheduled | Cart page | 2 days | 04 April 2019 8 00 AM | 05 April 2019 5 00 PM | 500 | tiến | 1
| Auto Scheduled | User site (after login) | 6 days | 06 April 2019 8 00 AM | 15 April 2019 5 00 PM | 500 |  | 1
| Manually Scheduled | User home page | 2 days | 06 April 2019 8 00 AM | 07 April 2019 5 00 PM | 500 | tiến | 1
| Manually Scheduled | User Edit Information page | 2 days | 08 April 2019 8 00 AM | 09 April 2019 5 00 PM | 500 | tiến | 1
| Manually Scheduled | User Favorite List | 2 days | 10 April 2019 8 00 AM | 11 April 2019 5 00 PM | 500 | tiến | 1
| Manually Scheduled | User Order History | 2 days | 12 April 2019 8 00 AM | 13 April 2019 5 00 PM | 500 | tiến | 1
| Manually Scheduled | User Order Detail | 2 days | 14 April 2019 8 00 AM | 15 April 2019 5 00 PM | 500 | tiến | 1
| Manually Scheduled | View product page | 2 days | 01 April 2019 8 00 AM | 02 April 2019 5 00 PM | 500 | Đạt | 1
| Manually Scheduled | Product detail page | 2 days | 03 April 2019 8 00 AM | 04 April 2019 5 00 PM | 500 | Đạt | 1
| Manually Scheduled | Contact page | 2 days | 05 April 2019 8 00 AM | 06 April 2019 5 00 PM | 500 | Đạt | 1
| Manually Scheduled | Track order page | 2 days | 07 April 2019 8 00 AM | 08 April 2019 5 00 PM | 500 | Đạt | 1
| Manually Scheduled | Introduce page | 1 day | 09 April 2019 8 00 AM | 09 April 2019 5 00 PM | 500 | Đạt | 1
| Manually Scheduled | News page | 1 day | 10 April 2019 8 00 AM | 10 April 2019 5 00 PM | 500 | Đạt | 1
| Manually Scheduled | News detail page | 1 day | 11 April 2019 8 00 AM | 11 April 2019 5 00 PM | 500 | Đạt | 1
| Auto Scheduled | Admin site | 8 days | 12 April 2019 8 00 AM | 23 April 2019 5 00 PM | 500 |  | 0.17000000000000001
| Manually Scheduled | Admin home page | 2 days | 16 April 2019 8 00 AM | 17 April 2019 5 00 PM | 500 | tiến | 1
| Manually Scheduled | Product management page | 2 days | 18 April 2019 8 00 AM | 19 April 2019 5 00 PM | 500 | tiến | 0.5
| Manually Scheduled | Customer Orders management page | 2 days | 20 April 2019 8 00 AM | 21 April 2019 5 00 PM | 500 | tiến | 0
| Manually Scheduled | Outcome Statistic page | 2 days | 22 April 2019 8 00 AM | 23 April 2019 5 00 PM | 500 | tiến | 0
| Manually Scheduled | Category management page | 2 days | 12 April 2019 8 00 AM | 13 April 2019 5 00 PM | 500 | Đạt | 0
| Manually Scheduled | Author management page | 2 days | 14 April 2019 8 00 AM | 15 April 2019 5 00 PM | 500 | Đạt | 0
| Manually Scheduled | Publishing Company management page | 2 days | 16 April 2019 8 00 AM | 17 April 2019 5 00 PM | 500 | Đạt | 0
| Manually Scheduled | User management page | 2 days | 18 April 2019 8 00 AM | 19 April 2019 5 00 PM | 500 | Đạt | 0
| Manually Scheduled | Contact management page | 2 days | 20 April 2019 8 00 AM | 21 April 2019 5 00 PM | 500 | Đạt | 0